## Work Flow
User | Facilities | E&U | Known Issues
User initiates a Minor Project Request
Facilities Planning receives the request and follows P&P #20 to make it actionable
| Plans are routed to E&U for comments |  | Extended design time often compresses review time to meet the schedule negotiated by the Facilities PM
|  | Plans information is entered into the E&U Plan Review Log and made available to each engineer. | No coincident reviews of plans between E&U staff.
|  | Each engineer will log the plans out; when the review is complete , log them back in and replace them back in rack. | Engineers availability varies, no back-up | If one engineer has the plans out, the other(s) have to wait | When an engineer has an unplanned absence the plans sits one their desks | Facilities proceeds with job without comments
|  | E&U Engineer(s) returns comments to Facilities Planning PM | No feedback loop to assure that the comments are incorporated into the design
| Facilities Planning completes the process described in P&P #20 |  | Comments do not always make their way from the DD's to the CD's | No feedback loop to assure that the comments are incorporated into the design | Change orders required to correct issues
END

## Fishbone
Computer |  | CAD versions |  | FP | Understands what but not how | A&E | Internal schedule not always known to FAU | User | Unfamiliar with required time | E&U | Schedules negotiated without respect to available man-hours
|  | No ability to comment with software |  |  | External schedules out of their control |  | Not completely familiar with FAU design criteria |  | Unfamiliar with paperwork flow |  | Irregular frequency of Requests
|  | No way to check files in and out |  |  | Accountable at Dean's level for schedule |  | Has to compile comments and transmit to his Eng Subs |  | Intersession's drive schedules |  | Regular workload varies
|  |  |  | Responsible for compiling all comments and transmitting them | Does not necessarily understand engineer's comments |  | No feedback that the changes have been implemented
|  |  | MACHINE |  |  |  |  | MAN
Plans for Minor Projects are finalized without corrections
|  |  | MATERIALS |  |  |  |  | METHOD
|  | Paper Plans |  |  |  |  | No way of documenting available time |  | Driven by FP's P&P 20
| Cost of Copies | [5 empty] | Individual reviews are individually time driven |  | Architect's process is outside our control
| Time to make copies | [5 empty] | Available Engineer's time might be coincident with the other reviewers' |  | No back up available for overflow or unplanned absences
[7 empty] | Several documents returned to PM, A&E to compile |  | Not able to comment with A&E's Software; has to be re-written several times

## Countermeasure Matrix
From the fishbone diagram, two general issues were uncovered:
1 | the scheduling of the engineering reviews
2 | the method that the information is transmitted and received
|  | Number | Issue | Number | Possible Countermeasure(s)
|  | 1 | the scheduling of the engineering reviews | 1.1 | Block out available time on a public calendar that allows the PM to schedule their project into that slot
|  |  |  | 1.2 | Negociate each job individually before any commitments to the user
|  |  |  | 1.3 | State a minimum lead time that we will be held accoutable for
|  |  |  | 1.4 | Use a scheduled "stand up review" for groups of projects so all comments are due at a specific time |  | (UF)
|  | 2 | the method that the information is transmitted and received | 2.1 | Common user platform for plan review similar to Microsoft Sharepoint | (UF)
|  |  |  | 2.1.1 | Already in use at the University, no cost
|  |  |  | 2.1.2 | Available through IRM
|  |  |  | 2.1.3 | Allows for version tracking
|  |  |  | 2.1.4 | Allow for source control