## Sheet1
No. | Test Item | Pass / Fail / Comment
1 | Verify Cable Cubby layout correct (VGA, single blank, RCAs, USBs, double blank, power) and height is reasonable to plug in USB device
2 | Verify Blu-Ray player is top in rack
3 | Verify PC is right below Blu-Ray player in rack
4 | Verify keypad labels are in correct location including custom labels LAPTOP/HDMI, AUX INPUT, DISC MENU, BLANK DISPLAY, EJECT
5 | Turn off power to rack to ensure all equipment is in default state before testing Wait 2 minutes before proceeding to allow control system to initialize program
6 | Verify that you can see the PC on the Sympodium when the system is off
7 | Verify that you can hear audio from PC when system is off
7 | Press MP-B20 keypad SYSTEM ON button Verify the SYSTEM OFF LED turns off Verify the SYSTEM ON LED blinks during startup Verify that all button presses are ignored during startup time Verify the SYSTEM ON LED turns on solid after system completes startup Verify the PC LED turns on after startup and the keypad backlight turns on for all rows
8 | Verify that room audio level was auto-set to 50% (observe volume level on MP-B20 keypad)
9 | Verify PC is shown on projection and Sympodium panel
10 | Verify PC resolution is set to 1366x768 and looks correct on Sympodium and Projector screen
11 | Verify PC audio comes through room speakers and is acceptable level w/o adjusting the Volume Knob
12 | Verify Volume Knob operation: can go from min level to max level in 2 complete turns Return to 50% when done
13 | Check that Sympodium works by using annotation pen
14 | Check that both Cable Cubby USB ports work - plug in flash drive and access it via the PC
15 | Verify that BluRay player automatically turned on when system was started up
16 | Press MP-B20 keypad BLU-RAY button Verify the BLU-RAY LED lights up
17 | Test BluRay deck control from keypad: EJECT
18 | Insert and Play BluRay disc
19 | Verify BluRay video is shown on Projector and Sympodium panel
20 | Verify BluRay audio comes through room speakers and is acceptable level
21 | Test BluRay deck transport controls from MB-B20 keypad: PAUSE, NEXT CHAPTER, PREVIOUS CHAPTER (momentary press of NEXT CHAPTER, PREVIOUS CHAPTER)
22 | Test BluRay deck transport controls from MB-B20 keypad: REWIND, FF (press and hold the previous/next chapter button to get rewind/ff)
23 | Test BluRay deck menu controls from MB-B20 keypad: MENU, UP, DOWN, LEFT, RIGHT, ENTER
24 | Verify that pushing MP-B20 keypad SYSTEM ON does nothing while system is already on
25 | Press MP-B20 keypad LAPTOP/HDMI button Verify the LAPTOP/HDMI LED lights up
26 | Connect Laptop via VGA/3.5mm to system via Cable Cubby
26 | Verify Laptop video is shown on Projector and Sympodium panel
27 | Verify Laptop audio comes through room speakers and is acceptable level
28 | Disconnect Laptop VGA/3.5mm and plug in HDMI now via Cable Cubby Should autoselect HDMI input
29 | Verify Laptop video is shown on Projector and Sympodium panel
30 | Verify Laptop audio comes through room speakers and is acceptable level
31 | Press MP-B20 keypad DOCCAM button Verify the DOCCAM LED lights up Verify the Doc Cam turns on automatically
32 | If DMPS IS NOT on FAU network (econtrol IPID is offline): Verify Doc Cam video is shown on Projector and Sympodium panel If DMPS IS on FAU network (econtrol IPID is online): Verify Doc Cam video is shown on Projector and that Epson viewer software starts up automatically on PC
33 | Press MP-B20 keypad AUX INPUT button Verify the AUX INPUT LED lights up
34 | Connect Composite/2RCA source to system via Cable Cubby
35 | Verify Aux Input video is shown on Projector and Sympodium panel
36 | Verify Aux Input audio comes through room speakers and is acceptable level
37 | Verify MP-B20 keypad BLANK DISPLAY button blanks the projector and NOT the Sympodium and does not mute audio (leave BLANK DISPLAY on)
38 | Press MP-B20 keypad SYSTEM OFF button Verify that SYSTEM ON LED turns off Verify the MP-B20 keypad backlight turn off for all rows Verify that SYSTEM OFF LED blinks during shutdown interval Verify that all button presses are ignored during shutdown time Verify all source equipment and projectors turn off Verify that SYSTEM OFF LED turns on solid after system completes shutting down
39 | Verify that BLANK DISPLAY setting was reset to off during shutdown (verify MP-B20 BLANK OFF LED turned off)
40 | Verify that shutdown time is long enough to allow projector to finish cool-down sequence I.e. user cannot turn system on while projector is still turning off
41 | Verify that room audio level was auto-set to 50%
42 | Verify PC is shown on Sympodium panel
43 | Verify system can be turned on by pressing any MP-B20 keypad Source button (instead of System On)
44 | Verify the same behavior for each source as described above
45 | While projector is On, push the DMPS SOFTWARE RESET button Verify that system goes to SYSTEM OFF state (observe MP-B20 keypad) Verify that system can be started up as usual while the projector is already on (Ensures a reset returns control system to known system off state; system state is not tracked by projector status)