## Phase One
GO-LIVE Linux Migration for completion by 03/9/12-3/11/12
# | Original Start Time | Projected Start Time | Actual Complete Time | Expected Complete Date | Estimated Hours | Who | ACTIVITY | DETAILS | Actual Complete Date
TASKS TO COMPLETE PRIOR TO February 25, 2012
1 |  |  |  | 2012-02-21 | N/A | Pat | Create Base Implementation Plan | UAS tasks and places for DBA updates. Forward to Chris. | 1900-01-01 05:46
2 |  |  |  | 2012-02-23 |  | Chris | Update Implementation plan with DBA tasks and time estimates |  | 2011-02-28
3 | [5 empty] | Ira | Identify Harvest packages and in what order to be implemented | Ira sends out notification to functional users a reminder to provide list | 2012-02-28
4 | [5 empty] | Pat/ Barbara | Create list of 3rd party notifications required | Touchnet / Royall, FACTS, AppWorx Schedule, TALX,
5 | [5 empty] | Pat/ Barbara | Create Schedule Proposal for AppWorx | EDI, FACTS, Royall, Grad App, COM load
6 | [5 empty] | Pat/ Barbara | Determine proposal for SSB downtime
7 |  |  |  | 2012-02-24 |  | Kay | Schedule Meeting with functional areas. Prior to meeting, distribute proposed timeline | 2/27-2/29?? | 2012-02-24
TASKS TO COMPLETE PRIOR TO March 3, 2012
8 | [5 empty] | Pat/ Barbara/ Kay | Complete proposed timeline to functional areas |  | 2012-02-27
9 | [5 empty] | Kay | Distribute proposed timeline to functional areas |  | 2012-02-28
10 |  |  |  |  | 5 days max | UAS/ /Touchnet/ AFTSS | Notification to Touchnet? |  | 2012-03-01
11 |  |  |  |  | 5 days max | AS/Nary | Notification for FACTS? |  | 2012-03-01
12 | [6 empty] | Notification for Royall?
13 |  |  |  | 2012-02-27 |  | Kay/Pat /Barbara /Chris/ Mehran | Meet with functional areas to review plan |  | 2012-02-29
14 |  |  |  | 2012-02-28 |  | Functional Areas | Approve plan |  | 2012-02-29
15 |  |  |  | 2012-03-02 |  | Kay | Announcements to Wendy & Communications | Also WordPress | 2012-03-02
16 |  |  |  | 2012-03-02 |  | Kay | Communication list to Functional Areas |  | 2012-03-05
17 |  |  |  | 2012-03-02 |  | AS/Jean | Provide Linux compatible version of AppWorx FAU_JAVAP shell to John |  | 2012-03-02
TASKS TO COMPLETE PRIOR TO March 9, 2012 5:00PM
18 |  |  |  | 3/1-3/7 |  | ALL | Funcational Area Checkout in TEST | Integrated Testing starts at 8:00am!!!!! | 2012-03-07
19 |  |  |  | 2012-03-07 |  | ALL | Functional Area Signoff in TEST instance |  | 2012-03-07
20 |  | 10am |  | 2012-03-08 |  | AS/Nary | Provide new IP (VPN) to FCAAS-FACTS | Switch over March 13th (Tues) Notify users that FACTS will not be available until 3/13 Request has been submitted to Systems | 2012-03-09
21 |  | 3pm |  | 2012-03-08 |  | AS/Barbara/Kay/ECS | SSB access unavailable | Provide list of netids for access to Wendy (SSB via MyFAU) | 2012-03-08
22 |  |  |  | 2012-03-08 |  | AS/Ira | Send final e-mail request for Linux dependent Harvest package approvals | User/Harvest package specific | 2012-03-08
23 |  | 4pm |  | 2012-03-08 |  | AS/Nary | Provide a list of the Student AppWorx jobs to be disabled |  | 2012-03-06
24 |  | 4pm |  | 2012-03-08 |  | AS/John | Provide a list of the HR/FR AppWorx jobs to be disabled |  | 2012-03-08
25 |  | 5:45pm |  | 2012-03-08 | 4 hrs | AS/Sue | Run EDI for last load before migration | Disable am and pm EDI job - Manually run (stop for 3-9 till ready) | 2012-03-09
26 |  | 8am |  | 2012-03-09 |  | Wendy | Post notification on MyFAU | SSB will be down at 3pm | 2012-03-06
27 |  | 1pm |  | 2012-03-09 |  | AS-Barb S | Run Admiss Stats reports | Report Caster job | 2012-03-09
28 |  | 2pm |  | 2012-03-09 |  | AS/John/Func Areas | Confirm AppWorx jobs were completed | This is related to the Friday's AppWorx jobs | 2012-03-09
29 |  | 3pm |  | 2012-03-09 |  | AS/David | Disable Transcript request via SSB | Backdoor - Alumni | 2012-03-09
30 |  | 3pm |  | 2012-03-09 |  | AS/OwlApp | Need to push last apps GR | Apps | 2012-03-09
31 |  | 3pm |  | 2012-03-09 |  | AFTSS/Touchnet | Need to stop Touchnet and Upay stores |  | 2012-03-09
32 |  | 3pm |  | 2012-03-09 |  | AS/Jean | Stop DARS Daemon | Stop DARS audit | 2012-03-09
33 |  | 3pm |  | 2012-03-09 | 2 | AFTSS/Marcia | Run AppWorx jobs to close out cashiering |  | 2012-03-09
34 |  | 3pm |  | 2012-03-09 |  | AS/OwlApp | Need to push last fees GR | Fees | 2012-03-09
35 |  | 3.31pm |  | 2012-03-09 |  | AS/Barbara K./Nary | Confirm automatic MAD push process is disabled | For OwlApp Fees/Apps | 2012-03-09
36 |  | 3:45pm |  | 2012-03-09 |  | AS/Jean | Stop Jserver | for OwlApp | 2012-03-09
37 |  | 4pm |  | 2012-03-09 |  | AS/Nary | Run Apps and Fee jobs | Final run of apps and fees | 2012-03-09
38 |  | 4pm |  | 2012-03-09 | 0.5 | AS/Pat | Disable faumgr cronjobs
39 |  | 4pm |  | 2012-03-09 |  | AS/Nick | Disable Fin Aid AppWorx jobs |  | 2012-03-07
40 |  | 3pm |  | 2012-03-09 | 0.5 | AS/John | Disable AppWorx jobs | From list | 2012-03-09
41 |  | 4pm |  | 2012-03-09 |  | All | All Harvest packages approved for promotion to production | UAS and Banner Functional users Only Linux required packages will be promoted to production per Ira's list. | 2012-03-09
42 |  | 4:15pm |  | 2012-03-09 | 1 | AS/Ira | Promote Harvest packages to production | per Ira's list | 2012-03-09
43 |  | 5:00pm |  | 2012-03-09 |  | Bob Pope | Confirm that Cashiering closeout is finished | OK to start the migration plan | 2012-03-09
44 |  | 5:00pm |  | 2012-03-09 | 0.25 | AS/David | Oracle Directory Objects | /export/home/-> /home | 2012-03-09
45 |  | 5:00pm |  | 2012-03-09 | 0.25 | AS/John | Install Linux compatible version of AW_BANNER to Production AppWorx |  | 2012-03-09
46 |  | 5:00pm |  | 2012-03-09 | 0.25 | AS/John | Install Linux compatible version of FAU_JAVAP to Production AppWorx |  | 2012-03-09
47 |  | 5:00pm |  | 2012-03-09 | 0.5 | AS/John | Export/Import AppWorx chains/modules from AppWorx2 TEST to AppWorx3 (PROD) as defined in the AppWorx instructions of the Harvest packages | 3/9: Send list of AppWorx Jobs to export/import rather than waiting for Harvest approve/promote task | 2012-03-09
FAUP Linux Migration begins March 9, 2012
|  | 5:00PM |  | 2012-03-09 |  |  | Banner FAUP unavailable
48 |  | 5:00PM |  | 2012-03-09 |  | DBA | Restrict all users from FAUP and grant Amy Cavasos and Stacey Semmel specific access to run several Financial reports | DBA sends e-mail to As, Amy and Stacey that they can now run their reports | 2012-03-09
49 |  | 5:00pm |  | 2012-03-09 | 0.5 | Stacey Semmel/ Amy Cavasos | Finance Reports for Data snapshot | Stacey is requesting is that she and Amy need to have access to Banner production, jobsub and e~Print after Banner is unavailable for everyone else. | 2012-03-09
50 |  | 5:30PM |  | 2012-03-09 |  | Stacey Semmel/ Amy Cavasos | Notifies DBAs and AS when done running Finance Reports | Reply All | 2012-03-09
51 |  | 5:35pm |  | 2012-03-09 |  | DBA | Restrict all users from FAUP |  | 2012-03-09
52 |  | 5:50pm |  | 2012-03-09 | 0.25 | DBA | Install Harvest packages | AS will provide DBA a list of Harvest packages | 2012-03-10
53 |  | 6:05pm |  | 2012-03-09 | 7 | DBA | Migrate old bannerprd to new bannerprd |  | 2012-03-10
54 |  | 1:05am |  | 2012-03-10 | 1 | DBA | Install AppWorx remote agent |  | 2012-03-10
55 |  | 1:05am |  | 2012-03-10 | 5min | DBA | Post migration DBA tasks | includes permissions, ACLs, etc. | 2012-03-10
56 |  | 6:45am |  | 2012-03-10 |  | DBA | e-mail AS when DBA tasks completed |  | 2012-03-10
57 | [5 empty] | Security - James | Any security tasks??? | Firewall settings???
58 | [5 empty] | DBA | FAUP in restricted mode for AS Pre-Checkout | AS will provide a list of users that will need access | 2012-03-10
|  | 7:00am |  |  |  |  | AS Pre-Checkout
59 |  | 7:00am |  |  | 1 | AS/Pat | Recompile evilp.pc | Send e-mail to OIT Linux list + Jason that beginning the Pre-Checkout tasks run $EXE_HOME/eviadm as Banner | 2012-03-10
60 |  |  |  |  | 1 | AS/Pat | Update Linux shell scripts | /usr/bin/mailx -> /bin/mailx /usr/bin/date -> /bin/date /export/home -> /home | 2012-03-10
|  | 8:00am |  |  |  |  | AS Checkout
61 |  | 8:00am |  |  | 0.5 | AS/AK | INB |  | 2012-03-10
62 |  |  |  |  | 0.5 | AS/AK | SSB |  | 2012-03-10
63 |  |  |  |  | 0.5 | AS/AK | Banner Reports/Jobsub |  | 2012-03-10
64 |  |  |  |  | 0.15 | AS/AK | e~Print |  | 2012-03-10
65 |  |  |  |  | 0.25 | AS/AK | Travel & Expense |  | 2012-03-10
66 |  |  |  |  | 0.5 | AS/AK | MyFAU On-line Faculty/Staff Directory refresh |  | 2012-03-10
67 |  | 8:00am |  |  | 0.5 | AS/Barbara K | OwlApp to Bannerprd | owlapp server | 2012-03-10
68 |  |  |  |  | 0.5 | AS/Barbara K | INB - SSB forms |  | 2012-03-10
69 |  |  |  |  | 0.5 | AS/Barbara K | DARS SSB and Client |  | 2012-03-10
70 |  | 8:00am |  |  | 0.15 | AS/Ira | BOG LAP process | FAUSFTP | 2012-03-10
71 |  | 8:00am |  |  | 0.15 | AS/Barbara S | GCIS extract |  | 2012-03-10
72 |  |  |  |  | 0.1 | AS/Barbara S | Virtual Orientation | IRMFTP | 2012-03-10
73 |  | 8:00am |  |  | 0.5 | AS/Bonnie | WebFocus |  | 2012-03-10
74 |  |  |  |  | 0.25 | AS/Bonnie | ReportCaster |  | 2012-03-10
75 |  |  |  |  | 0.25 | AS/Bonnie | Linux e-mail | via Banner, cronjobs, etc. | 2012-03-10
76 |  |  |  |  | 0.25 | AS/Bonnie | NWALT connection | sftp connection | 2012-03-10
77 |  |  |  |  | 0.5 | AS/Bonnie | BOG reports | create a file & sftp to workstation | 2012-03-10
78 |  | 8:00am |  |  | 0.5 | AS/Charles | Workflow | Run System Verification Workflow | 2012-03-10
79 |  |  |  |  | 0.5 | AS/Charles | Clean Address | INB/SSB | 2012-03-10
80 |  |  |  |  | 0.5 | AS/Charles | Intellecheck |  | 2012-03-10
81 |  |  |  |  | 0.5 | AS/Charles | Signature System |  | 2012-03-10
82 |  |  |  |  | 0.5 | AS/Charles | FAIR |  | 2012-03-10
83 |  |  |  |  | 0.5 | AS/Charles | MyFAU table refresh process |  | 2012-03-10
84 |  | 8:00am |  |  | 0.15 | AS/David | eCollege | irmftp | 2012-03-10
85 |  |  |  |  | 0.1 | AS/David | Library Patron | irmftp | 2012-03-10
86 |  |  |  |  | 0.15 | AS/David-Barb S | Blackboard connection | irmftp | 2012-03-10
87 |  | 8:00am |  |  | 0.15 | AS/Jean | FACTS /Jserver functionality | FACTS/Owlapp, FACTS AUDIT | 2012-03-10
88 |  |  |  |  | 0.5 | AS/Jean | Touchnet Transcript / Tuition | Touchnet server | 2012-03-10
89 |  |  |  |  | 0.15 | AS/Jean | BN Bookstore |  | 2012-03-10
90 |  |  |  |  | 0.15 | AS/Jean | Clearinghouse - SSB--update the path for wallet. | Clearinghouse site (SSB) | 2012-03-10
91 |  |  |  |  | 0.15 | AS/Jean | Luminis pin reset |  | 2012-03-10
92 |  |  |  |  | 0.15 | AS/Jean | unix file cleanup job | purge files periodically (appworx) | 2012-03-10
93 |  |  |  |  | 0.5 | AS/Jean & Lynn | COM Transcript | Script change (Harvest push) | 2012-03-10
94 |  | 8:00am |  |  | 0.5 | AS/John | Effort Certification |  | 2012-03-10
95 |  |  |  |  | 0.5 | AS/John | Labor Redistribution |  | 2012-03-10
96 |  |  |  |  | 1 | AS/John | AppWorx |  | 2012-03-10
97 |  |  |  |  | 1 | AS/John | PGP/encrypt/decrypt |  | 2012-03-10
98 |  |  |  |  | 0.5 | AS/John | ftp/sftp | irmftp.fau.edu, fausftp.fau.edu, etc | 2012-03-10
99 |  | 8:00am |  |  | 0.15 | AS/Keith | Clearinghouse - SSB as student |  | 2012-03-10
100 |  |  |  |  | 0.15 | AS/Keith | Test out Harvest
101 |  |  |  |  | 0.5 | AS/Keith | SSB / Webtailor | functionality | 2012-03-10
102 |  | 8:00am |  |  | 0.15 | AS/Lynn | Volunteer & Service Hours load | IRMFTP | 2012-03-10
103 |  |  |  |  | 0.15 | AS/Lynn | Video Streaming | IRMFTP | 2012-03-10
104 |  |  |  |  | 0.15 | AS/Lynn | Owlcard |  | 2012-03-10
105 |  | 8:00am |  |  | 0.15 | AS/Nary | Orientation | IRMFTP | 2012-03-10
106 |  |  |  |  | 0.15 | AS/Nary | VisualZen | IRMFTP (FAUSFTP) | 2012-03-10
107 |  |  |  |  | 0.15 | AS/Nary | Sevis? |  | 2012-03-10
108 |  | 8:00am |  |  | 2 | AS/Nick | TD Client | Old Bannerprd to New Bannerprd | 2012-03-10
109 |  |  |  |  | 1 | AS/Nick | Fin Aid Appworx job | Test out multiple parms, dynamic and letter creations | 2012-03-10
110 |  |  |  |  | 1 | AS/Nick | FM need calculations | Off site | 2012-03-10
111 |  | 8:00am |  |  | 0.15 | AS/Pat | Sleepwake |  | 2012-03-10
112 |  |  |  |  | 0.5 | AS/Pat | FormFusion |  | 2012-03-10
113 |  |  |  |  | 0.5 | AS/Pat | Update crontab | /export/home/-> /home | 2012-03-10
114 |  |  |  |  | 0.5 | AS/Pat | Update FormFusion Form definitions | W2, 1099, PO, CO, Third Party Billing, PHRDREG | 2012-03-10
115 |  |  |  |  | 1 | AS/Pat | Install Harvest remote agent |  | 2012-03-10
116 |  |  |  |  | 0.5 | AS/Ira | Test out Harvest | Create, promote, demote, checkout/checkin, etc | 2012-03-10
117 |  | 8:00am |  | 2012-03-10 | 1.5 | AS/Sue | EDI testscores | Loading backlog production - can run during users checkout
118 |  |  |  | 2012-03-10 | 1 | AS/Sue | EDI am job (decrypt of files from Texas, etc) | Loading backlog production - can run during users checkout | 2012-03-10
119 |  |  |  | 2012-03-10 | 2 | AS/Sue | EDI PM job (include ARP, encypt and SFTP to TEXAS) | Loading backlog production - can run during users checkout - following tables will not be available: SWAAPMCH, SWATTYP, SWATERR | 2012-03-10
120 |  | 11am |  | 2012-03-10 |  | AS/All | Each AS team member e-mails AS when their checkout is complete | Include task# & task activity | 2012-03-10
121 |  | 11am |  | 2012-03-10 |  | AS/Pat | e-mail DBA team to allow Amy and Stacey access to FAUP | After all AS team members have completed their checkout | 2012-03-10
122 |  | 11:15am |  | 2012-03-10 |  | DBA | Allow Amy and Stacey to access FAUP | Notifies AS, Amy and Stacey via e-mail | 2012-03-10
123 |  | 11:20am |  | 2012-03-10 |  | Amy Cavasos | Finance Reports for Data snapshot | Stacey is requesting is that she and Amy need to have access to Banner production, jobsub and e~Print after Banner is unavailable for everyone else. | 2012-03-10
124 |  | 11:50am |  | 2012-03-10 |  | Amy Cavasos | Notifies DBAs and AS when done running Finance Reports |  | 2012-03-10
125 |  | 11:55am |  | 2012-03-10 |  | DBA | Allow functional users to access FAUP and notifies AS |  | 2012-03-10
126 |  | 12:10pm |  | 2012-03-10 |  | AS/Pat | Sends e-mail to Functional users that FAUP is open and ready for their checkout | include status of any outstanding issues Reminder to e-mail AS when their checkout is complete | 2012-03-10
127 |  | 11am-12pm |  | 2012-03-10 | 3 | Functional Users | User verification testing in SSB and INB FAUP | Users can manually submit AppWorx jobs - no schedules are running at this time.
128 |  | 11am - 12pm |  | 2012-03-10 | 3 | Functional Users | Each Functional User sends e-mail to AS when their checkout is complete | Include any issues | 2012-03-10
129 |  | 4pm |  | 2012-03-10 |  | MAD/Rhian | Change OwlApp Pull/Push back to hourly | Change back to original hourly for fees and apps | 2012-03-12
130 |  | 6:30pm |  | 2012-03-10 | 1 | HR | HR will begin their testing |  | 2012-03-10
131 |  | 7:30pm |  | 2012-03-10 |  | AS/Pat | Sends e-mail to AS that all Functional users have completed their checkout | Waiting on HR | 2012-03-10
132 |  | 7:35pm |  | 2012-03-10 |  | AS/Pat | Send e-mail to DBA team to open FAUP for all to access | After HR completes their testing | 2012-03-10
133 |  | 7:40pm |  | 2012-03-10 | 0.25 | AS/John | Enable AppWorx jobs | Notify AS via e-mail | 2012-03-10
134 |  | 7:40pm |  | 2012-03-10 |  | Wendy | Enable SSB access | Notify AS via e-mail | 2012-03-10 | `
135 |  | 7:45pm |  | 2012-03-10 | 0.25 | AS/Keith | Open up SSB and Alumni backdoor | Notify AS via e-mail | 2012-03-10
136 |  | 8:00pm |  | 2012-03-10 |  | DBA | Opens FAUP access to all users | Notify AS via e-mail | 2012-03-10
137 |  | 8:10pm |  | 2012-03-10 |  | AS/Pat | Send e-mail to Functional Users & AS that FAUP is now available for all to access |  | 2012-03-10
138 | 7am | 8:10pm | 7am | 2012-03-12 |  |  | Banner LIVE in Linux | MONDAY MORNING 3/12/12
139 |  |  |  | 2012-03-12 | 0.5 | AS/Jean | Update jserver and resource.properties,start jserver,FACTS audit listener | Linux related changes
102 |  |  |  | 2010-02-15 |  | ALL | Go home and sleep!!