## Sheet1
Task ID | Task description | Assigned to | Start Date | End Date | Estimate
DEVL instance
1 | Setup Banner rules tables for Waitlist | Jeff H | 2011-03-14 | 2011-03-14
2 | Setup Banner web rules tables for Waitlist to show on SSB | Jeff H | 2011-03-14 | 2011-03-14
3 | Setup for select group of CRNS to use waitlist | Jeff H | 2011-03-14 | 2011-03-14 | 4 hrs
4 | Run SFRBWLP to send out emails - received 1 email | Jeff H | 2011-03-14 | 2011-03-14
5 | SFRBWLP - PARAMETER SEQUENCE NUMBER: sfrbwlp terminated with error | Jeff H | 2011-03-14 | 2011-03-14
6 | Download and apply SCT Fix - 1-FV04BI (2 sqls) | UAS / DBA | 2011-03-13 | 2011-03-13 | Need to install in DEVL
| Download and apply SCT Defects : 1-CQ3GB7, 1-8S5K9H, 1-BIB18L,1-D743WT, 1-BRA68R | UAS / DBA | 2011-03-25 | 2011-03-25 | Have retros to do because of the patches
| Retest the email sending | UAS/Jeff | 2011-03-25 | 2011-04-06
| Sleep-Wake process needed | UAS/Jeff | 2011-03-25 | 2011-03-25
| Setup three printers in DEVL and TEST instance | UAS-IRM | 2011-03-28 | 2011-03-28 | FAUP already done.
| Setup up the additional batch programs (appworx) - SFRBWLP, SFPWAIT(At end or before Term Reg), SFRWLRO (n/a), SSRASTZ (Setup CRN waitlist back to 0 - end waitlisting for CRN, At End of Drop/Add) | Jeff / Rich | 2011-03-29 |  | Manually run by registrar's office
TEST Instance
| Setup Banner rules tables for Waitlist | Jeff H | 2011-03-14 | 2011-03-14
| Setup Banner web rules tables for Waitlist to show on SSB | Jeff H | 2011-03-14 | 2011-03-14
| Setup for select group of CRNS to use waitlist | Jeff H | 2011-03-14 | 2011-03-14
| Run SFRBWLP to send out emails - 1 emails | Jeff H | 2011-03-15 | 2011-03-15
| Setup three printers in DEVL and TEST instance (updated FAUP) | UAS-IRM | 2011-03-28 | 2011-03-30 | FAUP already done.
| Unit testing | UAS - Jeff | 2011-03-28 | 2011-04-06 | Seems to be working
| Add new Znumber for Sleep/Wake email - registrar@fau.edu | Jeff H | 2011-04-05 | 2011-04-05 | Seems to be working
| Setup up the additional batch programs (appworx) - SFRBWLP, SFPWAIT(At end or before Term Reg), SFRWLRO (n/a), SSRASTZ (Setup CRN waitlist back to 0 - end waitlisting for CRN, At End of Drop/Add) | Jeff / Rich | 2011-03-29 |  | Manually run by registrar's office
FAUP Instance
| Setup Banner rules tables for Waitlist | Jeff H | 2011-03-14 | 2011-03-14
| Setup Banner web rules tables for Waitlist to show on SSB | Jeff H | 2011-03-14 | 2011-03-14
| Setup for select group of CRNS to use waitlist | Jeff H
| Run SFRBWLP to send out emails - 1 emails | Jeff H
| Installed 4 patches for Waitlist | DBA | 2011-03-31 | 2011-04-01
| Setup three printers in FAUP | UAS-IRM | 2011-03-28 | 2011-03-30
| Add new Znumber for Sleep/Wake email - registrar@fau.edu | Jeff H
| Setup up the additional batch programs (appworx) - SFRBWLP, SFPWAIT(At end or before Term Reg), SFRWLRO (n/a), SSRASTZ (Setup CRN waitlist back to 0 - end waitlisting for CRN, At End of Drop/Add) | Jeff / Rich | 2011-03-29 |  | Manually run by registrar's office