## owssvr
# | Environment | Task | Responsible Group | Task Status | Estimated Hours | Actual Start Date | Actual Finish | Due Date | % Complete | Notes
1 | AppWorx1,2,3 | Advance notice of AppWorx freeze | AS | Completed | .25 | 4124100% | 4124100% |  | 100%
2 | AppWorx2 | Notify users AppWorx unavailable | AS | Completed | .25 | 4124100% | 4124100% |  | 100% | Let users know that the job schedules will be turned off
3 | AppWorx2 | Turn off scheduled AppWorx jobs | AA | Completed | 1-2 | 4124600% | 4124600% | 4124600% | 100% | AA = AppWorx Admin
4 | AppWorx2 | Backup AppWorx | DBA | Completed | 1 | 4124600% | 4124600% | 4124600% | 100%
5 | AppWorx2 | Upgrade AppWorx to version 8 | DBA | Completed | 1 | 4124600% | 4124600% | 4124600% | 100%
6 | AppWorx2 | Full testing by all areas | ALL | In Progress | 3 days | 4124700% | 4124700% | 4124900% | 100% | Create a list of any special handling situations
7 | AppWorx2 | Signoff | All | Completed | 1 | 4125100% | 4125100% | 4125000% | 100%
8 | AppWorx1 | Backup AppWorx | DBA | Completed | 1 | 4125100% | 4125100% | 4125300% | 100%
9 | AppWorx1 | Upgrade AppWorx to version 8 | DBA | Completed | 1 | 4125100% | 4125100% | 4125300% | 100%
10 | AppWorx1 | Test | AA | Completed | 1 | 4125100% | 4125300% | 4125300% | 100% | Testing is just to be sure AppWorx is functioning correctly
11 | AppWorx1 | Signoff | AA | Completed | .25 | 4125400% | 4125400% | 4125300% | 100%
12 | AppWorx3 | Notify users scheduled AppWorx jobs will be turned off | AS | Not Started | .25 | 4125700% | 4125700% | 4125700% | 100%
13 | AppWorx3 | Turn off scheduled AppWorx jobs | AA | Not Started | 1-2 | 4125700% | 4125700% | 4126100% | 100%
14 | AppWorx3 | Backup AppWorx | DBA | Not Started | 1 | 4125800% | 4125800% | 4126100% | 100%
15 | AppWorx3 | Upgrade AppWorx to version 8 | DBA | Not Started | 1 | 4125800% | 4125800% | 4126100% | 100%
16 | AppWorx3 | Test sample selection | AA | Not Started | 1-2 | 4095500% | 4095600% | 4126100% | 100%
17 | AppWorx3 | Notify users AppWorx is available | AS | Not Started | .25 | 4095700% | 4095700% | 4126100% | 100%
18 | AppWorx3 | Turn on scheduled AppWorx jobs | AA | Not Started | 1-2 | 4095700% | 4095700% | 4126100% | 100%