## owssvr
# | Task | Assigned To | Task Status | Actual Start Date | Actual Finish | Due Date | % Complete | Notes
10 | Budget sends summer 2013 timeline | Jie Shi | Completed | 4133000% | 4133000% | 4133000%
20 | AS reviews timeline | Bonnie Li | Completed | 4133100% | 4133700% | 4133100%
30 | Budget revises timeline | Jie Shi | Completed | 4133100% | 4133700% | 4133100%
40 | AS checks with Payroll if TEST needs to be cloned | Patricia Espada | Completed | 4135400% | 4135400% | 4135400%
50 | Request DBA to clone TEST if needed | Patricia Espada | Canceled |  |  | 4135900% |  | no reponse from Payroll
60 | DBA to clone TEST |  | Canceled |  |  | 4136900%
70 | Budget sends AS sample faculty data file for testing | Jie Shi | Completed | 4136900% | 4137500% | 4136900% |  | from Rochelle at Provost's Office
80 | AS loads faculty test data file into a staging table in DEVL | Bonnie Li | Completed | 4137500% | 4137500% | 4136900%
90 | AS creates programs for testing in DEVL | Bonnie Li | Completed | 4137500% | 4137900% | 4136900%
100 | AS creates and inserts EPAF transactions into EPAF tables in DEVL | Bonnie Li | Completed | 4137900% | 4138000% | 4137200%
110 | AS e-mails a request to EPAF Admin to run the NOPEAMA process in DEVL, category codes: FACSCU & FACSCN | Bonnie Li | Completed | 4138000% | 4138000% | 4138000%
120 | EPAF Admin runs the NOPEAMA process in DEVL for categories FACSCU & FACSCN | Christine Smith | Completed | 4138000% | 4138000% | 4138000%
130 | AS reviews the EA Mass Apply Process report results in DEVL | Bonnie Li | Completed | 4138000% | 4138100% | 4138000%
140 | EPAF Admin reviews the EA Mass Apply Process report in DEVL | Christine Smith | Canceled |  |  | 4138100%
150 | EPAF Admin resolves any errors that occurred on the EA Mass Apply Process report in DEVL | Christine Smith | Canceled |  |  | 4138100%
160 | AS notifies Budget that the faculty summer contracts are now loaded into DEVL | Bonnie Li | Completed | 4138000% | 4138000% | 4138100%
170 | Budget verifies the faculty summer contracts in DEVL | Jie Shi | Canceled |  |  | 4138100%
180 | Budget sends AS the final faculty data file to be loaded in TEST | Jie Shi | Completed | 4137900% | 4138700% | 4138000% |  | Rochelle from the Provost's Office
190 | AS loads final faculty data file into a staging table in TEST | Bonnie Li | Completed | 4138800% | 4138800% | 4138100%
200 | AS creates and inserts EPAF transactions into EPAF tables in TEST | Bonnie Li | Completed | 4138800% | 4138800% | 4138700%
210 | UAS e-mails a request to EPAF Admin to run the NOPEAMA process in TEST, category codes: FACSCU & FACSCN | Bonnie Li | Completed | 4138800% | 4138800% | 4138700%
220 | EPAF Admin runs the NOPEAMA process in TEST for categories FACSCU & FACSCN | Christine Smith | Completed | 4138900% | 4138900% | 4138700%
230 | AS reviews the EA Mass Apply Process report results in TEST | Bonnie Li | Completed | 4138900% | 4138900% | 4138700%
240 | EPAF Admin reviews the EA Mass Apply Process report in TEST | Christine Smith | Canceled |  |  | 4138700%
250 | EPAF Admin resolves any errors that occurred on the EA Mass Apply Process report in TEST | Christine Smith | Completed | 4138900% | 4139000% | 4138800%
260 | AS notifies Budget that the faculty summer contracts are now loaded into TEST | Bonnie Li | Completed | 4138900% | 4138900% | 4138800%
270 | Budget verifies the faculty summer contracts in TEST | Jie Shi | Completed | 4138900% | 4139000% | 4138800% |  | notify Roshelle
280 | Budget notifies the business managers to verify the faculty summer contracts in TEST | Jie Shi | Completed | 4138900% | 4139000% | 4138800% |  | Rochelle
290 | AS removes earning records in TEST for earning code 009 created by the NOPEAMA | Bonnie Li | Completed | 4138900% | 4138900% | 4138800%
300 | AS requests Payroll to run the full payroll process in TEST | Bonnie Li | Completed | 4138900% | 4138900% | 4138800%
310 | Payroll runs a full payroll process in TEST | Ann Lanza-Waldron | Completed | 4138900% | 4139000% | 4138900%
320 | AS requests EPAF Admin to send out an annoucement to the EPAF users that the EPAF system will be unavailable in FAUP | Bonnie Li | Completed | 4139000% | 4139000% | 4139000%
330 | AS Self-Service Admin. is notified to disable WebTime Entry and E-PAF links in FAUP | David Correa | Completed | 4139000% | 4139000% | 4139300%
340 | HR EPAF Admin sends out the annoucement to the EPAF users that the EPAF system will be unavailable in FAUP | Christine Smith | Completed | 4139000% | 4139000% | 4139300%
350 | Budget gives AS a list of deletions and updates for the faculty data file | Jie Shi | Completed | 4139300% | 4139400% | 4139300% |  | update posn, suffix, and delete id/posn from Rochelle
360 | AS updates the faculty data file and loads into the staging table in FAUP | Bonnie Li | Completed | 4139300% | 4139400% | 4139300% |  | updated posn, suffix, and delete
370 | AS Self-Service Admin. disables WebTime Entry and E-PAF links in FAUP | David Correa | Completed | 4139400% | 4139400% | 4139400%
380 | AS creates and inserts EPAF transactions into EPAF tables in FAUP | Bonnie Li | Completed | 4139400% | 4139400% | 4139400%
390 | AS e-mails a request to EPAF Admin to run the NOPEAMA process in FAUP, category codes: FACSCU & FACSCN | Bonnie Li | Completed | 4139400% | 4139400% | 4139400%
400 | EPAF Admin runs the NOPEAMA process in FAUP for categories FACSCU & FACSCN | Christine Smith | Completed | 4139400% | 4139400% | 4139400%
410 | AS reviews the EA Mass Apply Process report results in FAUP | Bonnie Li | Completed | 4139400% | 4139400% | 4139400%
420 | HR EPAF Admin reviews the EA Mass Apply Process report in FAUP | Christine Smith | Completed | 4139400% | 4139400% | 4139400%
430 | HR EPAF Admin resolves any errors that occurred on the EA Mass Apply Process report in FAUP | Christine Smith | Completed | 4139400% | 4139400% | 4139400%
440 | AS Self-Service Admin. is notified to enable WebTime Entry and E-PAF links in FAUP | David Correa | Completed | 4139400% | 4139400% | 4139400%
450 | AS Self-Service Admin. enables WebTime Entry and E-PAF links in FAUP | David Correa | Completed | 4139400% | 4139400% | 4139400%
460 | AS notifies HR EPAF Admin that EPAF system is available in production | Bonnie Li | Completed | 4139400% | 4139400% | 4139400%
470 | AS notifies Budget that the faculty summer contracts are now loaded into FAUP | Bonnie Li | Completed | 4139400% | 4139400% | 4139400%
480 | AS removes earning records in FAUP for earning code 009 created by the NOPEAMA | Bonnie Li | Completed | 4139400% | 4139400% | 4139400%
490 | Budget verifies contracts in FAUP | Jie Shi | Completed | 4139400% | 4139400% | 4139400% |  | Rochelle
500 | Budget notifies the business managers to verify the faculty summer contracts in FAUP | Jie Shi | Completed | 4139400% | 4139400% | 4139400% |  | Rochelle