## Requirements-General
Line # | General Requirements
1 | Shall be to reset all rack equipment and classroom touchpanel by turning off power to equipment rack
2 | Touchpanel shall be powered over Cresnet from equipment rack, instead of powered locally
3 | Shall be able to start system up regardless of state of room projectors (to correct problem where projectors must be turned off when performing a system reset)
4 | System shall support 3 modes of operation, selectable from Touchpanel: Local Class (for classroom presentation and Echo360 recording use) VC Originate (teaching from this classroom to other connected classrooms, at other campuses) VC Receive (watching/interacting with a class taught from another campus)
5 | Shall display same content on both projectors in dual-projector rooms to minimize
6 | Shall use rear flat panel in Local Class mode as a confidence monitor (connected to CaptureHD conf monitor output), see display state layout diagram for specifics
7 | Shall use multiple student cameras (and associated mic zones) depending on room width, to minimize camera movement seen by far-end students
8 | Shall be able to set student camera preset locations on Touchpanel, by using Technician page accessible by passcode (digit equivalent of 'oitonly' on phone keypad)
9 | Touchpanel shall only have 1 Volume Slider labeled "Room Audio", which only affects program audio out of the program speakers
10 | Room Audio slider shall have no effect on program/speech audio level sent to Echo360, Crestron CaptureHD, or VC CODEC
11 | Touchpanel backlight shall remain on for 2 hours after it is 'woken up' by a user
12 | Touchpanel shall show text of the mode the system is currently in (VC Originate, VC Receive, Local Class) Shall be located within each content tab, above the horizontal bar
13 | Touchpanel shall have a Mute button which, mutes Program Audio to room speakers, Codec and Echo 360 (no effect on Speech audio)
14 | Touchpanel Blank Projection button shall blank video to in-room projectors
15 | Blank Projection shall blank Content video signal going to Echo360 and VC CODEC (provide same behavior to remote students as local students)
16 | Blank Projection shall not affect audio in the AV system at all
17 | Blank Projection shall not blank video signal going to Sympodium display
18 | Touchpanel VC Receive mode shall have no tabs (no source selection), no Blank Projection button, and no Mute button Shall support 2 display layout states- far-end video with no content, far-end video with content; see display state layout diagram for specifics Shall provide buttons to lock a particular camera view to send to remote side: Instructor Camera/Left Student Camera Only/Right Student Camera Only/etc. Shall provide button to return camera switching behavior to automatic mode: Automatic Camera Mode
19 | Touchpanel VC Originate mode shall not include Blu-Ray due to content protection issues (only exists in Local Class mode)
20 | Touchpanel VC Originate mode shall include a Cameras Only tab See display layout state diagram for video display specifics Shall provide buttons on Cameras Only tab for forcing camera view to send to remote side: Instructor Camera Only/Left Student Camera Only/Right Student Camera Only/etc. Shall provide button on Cameras Only tab to return camera switching behavior to automatic mode: Automatic Camera Mode Upon selecting a different source tab, will return to VC Originate w/ Content display state layout
21 | Shall provide FAU technicians the ability to remotely control the AV system via an ActiveX web-based control
22 | Shall reserve an IPID within room control program for the Xpanel
23 | Touchpanel shall have a Mute Mics button Next to Room Audio slider Pressing this shall mute ALL student and instructor mics (desktop gooseneck mic and wireless mics) Shall blank all flat panel displays and projectors in room (make it obvious to instructors that room is in 'privacy' mode) Touchpanel layout shall be replaced by one large button with text - "Mics are Muted - Press Screen to Continue Session" which un-mutes all mics, returns displays to un-blanked state
24 | Control system shall keep current time by regularly syncing with internet-based network time service
25 | Shall provide sound reinforcement in classroom from student and instructor classroom mics (provides confirmation to mic user that mic is active)
26 | Shall create 2 speech speaker zones within audience area: left side of audience area, right side of audience area
27 | Audio from mics in zone 1 shall only be audible in zone 2 and vise versa, to prevent feedback (Mix-Minus)
28 | In-room student mic speech reinforcement shall be just audible enough to provide confirmation to mic user that his/her mic is active
29 | In Local Class mode, only Instructor Gooseneck and Revolab mic audio will be sent to Echo appliance/VC Codec (no student audio)
30 | In-room instructor mic speech reinforcement (both Gooseneck and Revolabs mics) shall be just audible enough to provide confirmation to mic user that his/her mic is active
31 | With Touchpanel Room Audio slider set at 50%, room program audio shall be loud enough to be usable for a full class without adjustment
32 | Shall use the PC playing back an audio clip with Windows mixer set at 50% as the reference
33 | System shall reset all student mics when started up in any mode (should have no active student mics when system starts up)
34 | Shall configure DigitalMedia switcher to accept the following input resolutions:
35 | Laptop input: 1024x768, 1280x720, 1280x800, 1360x768, all @ 60 Hz
36 | In-room PC resolution: 1360x768 @ 60 Hz
37 | Blu-Ray player: 1280x720 @ 60 Hz
38 | Document Camera: 1280x720 @ 60 Hz
39 | Shall configure DM output scalers for the following resolutions:
40 | To Sympodium panel: Just pass native resolution of incoming signal, no scaling [Changed from 1366x768 b/c of 'fuzzy' look on Sympodium panel]
41 | To Projectors: 1280x800 @ 60 Hz, Stretch Mode [Native resolution of these displays]
42 | To Flat-Panel Displays: 1920x1080 @ 60 Hz, Stretch Mode [Native resolution of these displays]
43 | Shall install lectern rack equipment such that Blu-Ray player is in the topmost space in the rack, followed by the room's PC
44 | Shall setup Revolabs mics as follows:
45 | Shall use a single channel output from both mics
46 | Shall disable the local mute capability
47 | Shall set the mics to work with a 25' transmit range
punchlist items for CM125/CM130/NU202:
Changing modes (local class --> vc originate --> local class) messes up state of flat panels
Set admin and user passwords for the AV2

## Requirements-Functional
Line # | Action | Touchpanel | Room Audio | Projectors | Rear Flat Panel | Front Flat Panels | CODEC | Echo360 | Crestron CaptureHD | Other
Local Class Mode Functionality
1 | From System Off, Press Local Class Button | Show wait screen until projectors all the way turned on Show the PC Tab | Set to 50% | Turn on, Show PC | Turn On, Show CaptureHD Confidence Monitor output | Turn Off, No Video | Send PC video and audio Send only Instructor Camera video Send only Instructor Gooseneck/Revolabs Mic audio | Send PC video and audio Send only Instructor Camera video Send only Instructor Gooseneck/Revolabs Mic audio | Send PC video and audio Send the Instructor Camera Composite video Send only Instructor Gooseneck/Revolabs Mic audio | Turn on BluRay deck when system turns on
2 | Press Blu-Ray tab | Show the Blu-Ray tab |  | Show Blu-Ray video | Show no video (Blank/Mute Video) | - | Send Blu-Ray video/audio (Only works with DVDs) Send only Instructor Camera video Send only Instructor Gooseneck/Revolabs Mic audio | Send Blu-Ray video/audio (Only works with DVDs) Send only Instructor Camera video Send only Instructor Gooseneck/Revolabs Mic audio | Send Blu-Ray video/audio (Only works with DVDs) Send the Instructor Camera Composite video Send only Instructor Gooseneck/Revolabs Mic audio
3 | Press Doc Cam tab | Show the Doc Cam tab |  | Show Doc Cam video | Show CaptureHD Confidence Monitor output | - | Send Doc Cam video Send only Instructor Camera video Send only Instructor Gooseneck/Revolabs Mic audio | Send Doc Cam video Send only Instructor Camera video Send only Instructor Gooseneck/Revolabs Mic audio | Send Doc Cam video Send the Instructor Camera Composite video Send only Instructor Gooseneck/Revolabs Mic audio | Power up Doc Cam when selected
4 | Press Laptop tab | Show the Laptop tab |  | Show Doc Cam video | Show CaptureHD Confidence Monitor output | - | Send Laptop video and audio (Auto select HDMI or VGA) Send only Instructor Camera video Send only Instructor Gooseneck/Revolabs Mic audio | Send Laptop video and audio (Auto select HDMI or VGA) Send only Instructor Camera video Send only Instructor Gooseneck/Revolabs Mic audio | Send Laptop video and audio (Auto select HDMI or VGA) Send the Instructor Camera Composite video Send only Instructor Gooseneck/Revolabs Mic audio
5 | Press PC tab | Show the PC tab |  | Show PC video | Show CaptureHD Confidence Monitor output | - | Send PC video and audio Send only Instructor Camera video Send only Instructor Gooseneck/Revolabs Mic audio | Send PC video and audio Send only Instructor Camera video Send only Instructor Gooseneck/Revolabs Mic audio | Send PC video and audio Send the Instructor Camera Composite video Send only Instructor Gooseneck/Revolabs Mic audio
6 | Press Blank Projection button | Turn on the Blank Projection Button |  | Show no video, black screen | Show CaptureHD Confidence Monitor output | - | Send no source video/audio Send only Instructor Camera video Send only Instructor Gooseneck/Revolabs Mic audio | Send no source video/audio Send only Instructor Camera video Send only Instructor Gooseneck/Revolabs Mic audio | Send no source video/audio Send the Instructor Camera Composite video Send only Instructor Gooseneck/Revolabs Mic audio | Do not blank Sympodium
7 | Press Mute button (with Room Audio slider) | Turn on the Mute Button | No audio from front (program audio) speakers | - | - | - | - | Send no source audio Send Active Camera video Send only Instructor Gooseneck/Revolabs Mic audio | Send no source audio Send the Instructor Camera Composite video Send only Instructor Gooseneck/Revolabs Mic audio | Press Mute button again to undo program audio mute behavior
8 | Press Mute button again (unmute) | Turn off the Mute Audio Button | Enable audio to front program audio speakers | - | - | - | - | Restore source audio | Restore source audio
9 | Adjust Room Audio Slider | Shows current level | Only adjusts room audio | - | - | - | - | No change to audio level | No change to audio level | Note there is only 1 slider now
10 | Press Power Off / Home button | Show System Off/Mode Switch confirmation page |  | - | - | - | - | - | -
11 | Press Shutdown button | Show wait screen until projectors all the way turned off Then show class mode page | Set to 50% | Turn off | Turn Off | - | Send no video/audio | Send no video/audio | Send no video/audio | Turn off Doc Cam, Turn off Blu-Ray
[10 empty] | - | -
VC Originate Mode Functionality
12 | From System Mode screen, Press VC Originate Button (no content transmitted yet) | Show wait screen until projectors all the way turned on Show the 'Select a source' screen | Set to 50% | Turn on, Show CODEC Remote Main Video | Turn On, Show CODEC Remote Main camera video | Turn On, Show CODEC Self-View (Currently-Active Camera) | Default to no content (just camera video) Send the Active Camera video Send the Active Mic audio | Default to no content Send the Active Camera video Send the Active Mic audio | Default to no content Send the Instructor Camera Composite video Send the Active Mic audio | BluRay deck does not turn on automatically in this mode Active Camera starts out as Instructor Camera
13 | Press PC tab (now transmitting content) | Show the PC tab |  | Show PC video (NOT passed through CODEC) | Show CODEC Remote Main camera video, Self-View in PIP (Currently-Active Camera) | Show CODEC Remote Main camera video, Self-View in PIP (Currently-Active Camera) | Send PC video and audio Start DuoSource Send the Active Camera video Send the Active Mic audio | Show PC video (NOT passed through CODEC) Send the Active Camera video Send the Active Mic audio | Show PC video (NOT passed through CODEC) Send the Instructor Camera Composite video Send the Active Mic audio
14 | Press Doc Cam tab | Show the Doc Cam tab |  | Show Doc Cam video (NOT passed through CODEC) | Show CODEC Remote Main camera video, Self-View in PIP (Currently-Active Camera) | Show CODEC Remote Main camera video, Self-View in PIP (Currently-Active Camera) | Send Doc Cam video Start DuoSource Send the Active Camera video Send the Active Mic audio | Send Doc Cam video (NOT passed through CODEC) Send the Active Camera video Send the Active Mic audio | Send Doc Cam video Send the Instructor Camera Composite video Send the Active Mic audio | Power up Doc Cam when selected
15 | Press Laptop tab | Show the Laptop tab |  | Show Laptop video (NOT passed through CODEC) | Show CODEC Remote Main camera video, Self-View in PIP (Currently-Active Camera) | Show CODEC Remote Main camera video, Self-View in PIP (Currently-Active Camera) | Send Laptop video and audio (Auto select HDMI or VGA) Start DuoSource Send the Active Camera video Send the Active Mic audio | Send Laptop video and audio (NOT passed through CODEC) (Auto select HDMI or VGA) Send the Active Camera video Send the Active Mic audio | Send Laptop video and audio (Auto select HDMI or VGA) Send the Instructor Camera Composite video Send the Active Mic audio
16 | Press Blank Projection button | Turn on the Blank Projection Button |  | Show no video, black screen | - | - | Send no source video/audio Send the Active Camera video Send the Active Mic audio | Send no source video/audio Send the Active Camera video Send the Active Mic audio | Send no source video/audio Send the Instructor Camera Composite video Send the Active Mic audio
17 | Press Blank Projection button again (unblank) | Turn off the Blank Projection Button |  | Return to previous state | - | - | Return to previous state | Return to previous state | Return to previous state
18 | Press Mute button (with Room Audio slider) | Turn on the Mute Button | No audio from front (program audio) speakers | No change | - | - | - | Send no source audio Send Active Camera video Send only Instructor Gooseneck/Revolabs Mic audio | Send no source audio Send the Instructor Camera Composite video Send only Instructor Gooseneck/Revolabs Mic audio | Press Mute button again to undo program audio mute behavior
19 | Press Mute button again (unmute) | Turn off the Mute Audio Button | Enable audio to front program audio speakers | No change | - | - | - | Restore source audio | Restore source audio
20 | Adjust Room Audio Slider | Shows current level | Only adjusts room audio |  | - | - | - | - | No change to audio level | Note there is only 1 slider now
21 | Press Power Off / Home button | Show System Off/Mode Switch confirmation page |  | No change | - | - | - | - | No change
22 | Press Shutdown button | Show wait screen until projectors all the way turned off Then show class mode page | Set to 50% | Turn off | Turn Off | Turn Off | Send no video/audio | Send no video/audio | Send no video/audio | Turn off Doc Cam, Turn off Blu-Ray
[10 empty] | - | -
VC Receive Mode Functionality
23 | From System Mode screen, Press VC Receive Button | Show wait screen until projectors all the way turned on Show the VC Receive tab | Set to 50% | Turn on, Show CODEC Remote Content |  | Turn On, Show CODEC Remote Main Video | Send the Active Camera video Send the Active Mic audio | No actions | No actions | No Source tabs, no Advanced Tab Active Camera is student camera, wide shot of room Instructor Camera is not available in this mode
24 | (No incoming content from far end, just incoming video) |  |  | Show CODEC Remote Main camera video | Show CODEC Remote Main camera video | Show CODEC Self-View (Currently-Active Camera)
25 | (Incoming duosource content video from far-end) |  |  | Show CODEC Remote Content | Show CODEC Remote Main camera video, Self-View in PIP (Currently-Active Camera) | Show CODEC Remote Main camera video, Self-View in PIP (Currently-Active Camera)
26 | Adjust Room Audio Slider | Shows current level | Only adjusts room audio |  | - | - | No change to audio level | No actions | No actions | Note there is only 1 slider now
27 | Press Left Student Camera Only button | Shows current level | Only adjusts room audio |  |  |  | No change to audio level | No actions | No actions | Note there is only 1 slider now
28 | Press Power Off / Home button | Show System Off/Mode Switch confirmation page |  | No change |  | No change | No change | No change | No change
29 | Press Shutdown button | Show wait screen until projectors all the way turned off Then show class mode page | Set to 50% | Turn off |  | No change | Send no video/audio | Send no video/audio | Send no video/audio | Turn off Doc Cam, Turn off Blu-Ray

## LaterUse RoomView-->Processor (hidden)
Join Type | Join Number | Built Into RoomView vs. Custom Signal | Description of Signal
Digital | 81 | Custom | Control System Hardware Reset
Digital | 80 | Custom | Control System Program Reset
Digital | 5 | Built-In | Display1 Power On/Off
Digital | 3 | Built-In | System Power On/Off
Serial | 4 | Built-In | GMT-based time of day from RV server (for RV-processor time sync)

## LaterUse Processor-->RoomView (hidden)
Join Type | Join Number | Built Into RoomView vs. Custom Signal | Description of Signal | Control Program Behavior
Analog | 51 | Custom | Display1 Filter Hours from Projector [If projector model supports capability]
Analog | 52 | Custom | Display1 Filter Hours from Projector as % of Total Filter Life [If projector model supports capability]
Analog | 2 | Built-In | Display1 Lamp Hours from Projector [Current Label: Display Usage, Max=2000]
Analog | 50 | Custom | Display1 Lamp Hours from Projector as % of Total Lamp Life
Analog | 55 | Custom | Display2 Filter Hours from Projector [If projector model supports capability]
Analog | 56 | Custom | Display2 Filter Hours from Projector as % of Total Filter Life [If projector model supports capability]
Analog | 53 | Custom | Display2 Lamp Hours from Projector
Analog | 54 | Custom | Display2 Lamp Hours from Projector as % of Total Lamp Life
Analog | 3 | Built-In | Error Alert Severity Number (Sent when projector status message is set)
Serial | 50 | Custom | Current Action | Text of Current System State: Off, Starting Up, Show PC, Show Laptop, Show Doc Cam, Show VHS/DVD, Show BluRay, Shutting Down * Also tie to a Make String Permanent symbol
Serial | 5 | Built-In | Device Usage Data Text | Use Crestron module, See next tab for detail
Serial | 51 | Custom | Display1 Error Status (example: result on ERR? request, as error description text; return 00 if no error)
Serial | 52 | Custom | Display2 Error Status (example: result on ERR? request, as error description text; return 00 if no error)
Serial | 2 | Built-In | Error Message Text (projector status message)

## SystemStates (hidden)
System State Text
Presentation Classroom | VC Classroom | VC Conference Room
Off | Off | Off
Starting Up | Starting Up | Starting Up
Show PC | Show PC | Show PC
Show Laptop-Analog | Show Laptop-Analog | Show Laptop-Analog
Show Laptop-Digital | Show Laptop-Digital | Show Laptop-Digital
Show Doc Cam | Show Doc Cam | Show Doc Cam
Show BluRay | Show BluRay | Show BluRay
Show ExternalAV | VC-O: Video Only | VC: Show Video Only
Shutting Down | VC-O: Show PC | VC: Show PC
| VC-O: Show Laptop-Analog | VC: Show Laptop-Analog
| VC-O: Show Laptop-Digital | VC: Show Laptop-Digital
| VC-O: Show VC O | VC: Show VC
| VC-O: Show BluRay | VC: Show BluRay
| VC Receive | Shutting Down
Shutting Down

## TestPlan-LocalClass
Line | Test Item | Pass / Fail / Comment
Local Class Mode Testing
1 | Begin an Ad-Hoc Echo appliance recording [Echo appliance monitor] Connect to room's VC Codec [Bridge or Movi Call]
2 | Go to Equipment Rack and press Record on Crestron CaptureHD
3 | Go to classroom instructor station
4 | Verify Cable Cubby layout correct (VGA, single blank, RCAs, USBs, double blank, power) and height is reasonable to plug in USB device
5 | Verify Blu-Ray player is top in instructor station rack
6 | Verify PC is right below Blu-Ray player in instructor station rack
7 | Check that Sympodium works by using annotation pen
8 | Check that both Cable Cubby USB ports work - plug in flash drive and access it via the PC
9 | Verify that you can see the PC on the Sympodium when the system is off
10 | Verify that you can hear audio from PC when system is off
11 | Press Local Class button on Touchpanel Verify the Touchpanel goes into a 'please wait' screen during startup Verify the Touchpanel goes to PC Tab after startup process is done Verify the text "Local Class" shows near the top of the Touchpanel Verify projectors turn/stay on Verify rear flat panel turns/stays on Verify front flat panels turn/stay off
12 | Verify that room audio level was auto-set to 50% (observe volume level on Touchpanel)
13 | Verify PC resolution is set to 1360x768 and looks correct on Sympodium and Projector screen
14 | Verify on PC that no resolutions above 1360x768 are selectable
15 | Verify that displays match the display state layout diagram for Local Class
16 | Verify PC shows on projection (Native PC Signal, Not from Codec) and Sympodium panel Verify by disconnecting VC call [Bridge or Movi] - should see no interruption to signal on projectors and to Echo appliance After verification, reconnect VC call
17 | On the PC, play back audio clip at http://tiny.cc/audiotest while the Windows mixer is set at 50% on the PC Verify audio is appropriately loud for classroom while Touchpanel slider is at 50%
18 | Verify that PC video is sent to Echo appliance [confirm via Echo appliance monitor] Verify that PC audio is sent to Echo appliance [confirm via Echo appliance monitor]
19 | Verify that PC video is sent to VC Codec [confirm via Bridge or Movi Call] Verify that PC audio is sent to VC Codec [confirm via Bridge or Movi Call]
20 | Verify that rear flat panel shows Confidence Monitor from Crestron CaptureHD (PC video w/ Instructor Camera video PIP)
21 | Verify that other flat panels are off, showing no content or video
22 | Verify that Instructor Gooseneck Mic/Revolab mic audio is sent to VC Codec [confirm via Bridge or Movi Call] Verify that Instructor Gooseneck Mic/Revolab mic audio is sent to Echo appliance [confirm via Echo appliance monitor]
23 | Verify that Instructor Camera video is sent to Echo appliance [confirm via Echo appliance monitor]
24 | Verify that Instructor Camera video is sent to VC Codec [confirm via Bridge or Movi Call]
18 | With test audio still playing back, press Touchpanel Mute button (near Room Audio slider): Verify no PC Audio goes to Program Audio speakers (front of room speakers) Verify no PC Audio goes to VC Codec [confirm via Bridge or Movi call] Verify no PC Audio goes to Echo appliance [confirm via Echo appliance monitor] Verify that Gooseneck/Revolab mic audio is still sent to room speakers Verify that Gooseneck/Revolab mic audio is still sent to VC Codec [confirm via Bridge or Movi Call] Verify that Gooseneck/Revolab mic audio is still sent to Echo appliance [confirm via Echo appliance monitor] Press Touchpanel Mute button again to return audio to fully working state
19 | At Touchpanel, press Mute Mics button Verify projectors are blanked Verify no Gooseneck/Revolab mic audio is sent to VC Codec [confirm via Bridge or Movi Call] Verify no Gooseneck/Revolab mic audio is sent to Echo appliance [confirm via Echo appliance monitor] Verify that Touchpanel only shows a screen with "Mics are Muted - Press Screen to Continue Session"
20 | Press Mute Mics button again to disable this function Verify that Touchpanel returns to it's previous source screen Verify that projectors show content again Verify that Gooseneck/Revolab mic audio is sent to VC again [confirm via Bridge or Movi Call] Verify that Gooseneck/Revolab mic audio is sent to Echo appliance [confirm via Echo appliance monitor]
21 | Verify student mics are not usable in Local Class mode (no audio sent to VC Codec or Echo360) Activate a student mic on left side of room Verify no audio from this student mic is sent to VC Codec [confirm via Bridge or Movi call] Verify no student camera video is sent to VC Codec [confirm via Bridge or Movi call] Verify no audio from this student mic is sent to Echo appliance [confirm via Echo appliance monitor] Verify no student camera video is sent to Echo appliance [confirm via Echo appliance monitor] Verify that the student mic audio is not audible in the rest of the room Deactivate student mic Go to right side of room and select a student mic, repeat above procedure
22 | Press Blu-Ray tab on Touchpanel
23 | Test BluRay deck control from Touchpanel by pressing Eject button
24 | Insert and Play a BLU-RAY disc
25 | Verify Blu-Ray player video shows on Projector and Sympodium panel
26 | Verify Blu-Ray player audio comes through room speakers and is acceptable level while Room Audio slider is at 50%
27 | Test BluRay deck transport controls from Touchpanel: Pause, Rewind, FForward, Next Chapter, Previous Chapter
28 | Test BluRay deck menu controls from Touchpanel: Menu, Up, Down, Left, Right, Enter
29 | NOTE: Blu-Ray/DVD Content will not be seen via Echo appliance or VC Codec
30 | Press Laptop tab on Touchpanel Verify you see the following text on the Laptop tab: "Please use one of the following resolutions with your laptop: 1024x768, 1280x720, 1280x800, 1360x768"
31 | Connect Laptop via VGA/3.5mm to system via Cable Cubby
32 | Verify on laptop that 1024x768, 1280x720, 1280x800, 1360x768 resolutions are selectable, no higher resolutions are selectable
33 | Verify Laptop shows on projection (Native PC Signal, Not from CODEC) and Sympodium panel Verify by disconnecting VC call [Bridge or Movi] - should see no interruption to signal on projectors and to Echo appliance After verification, reconnect VC call
34 | Verify that Laptop video is sent to Echo appliance [confirm via Echo appliance monitor] Verify that Laptop audio is sent to Echo appliance [confirm via Echo appliance monitor]
35 | Verify that Laptop video is sent to VC Codec [confirm via Bridge or Movi Call] Verify that Laptop audio is sent to VC Codec [confirm via Bridge or Movi Call]
36 | Verify that rear flat panel shows Confidence Monitor from Crestron CaptureHD (Laptop video w/ Instructor Camera video PIP)
37 | On the Laptop, play back an audio clip at http://tiny.cc/audiotest while the Windows mixer is set to 50% on the Laptop Verify audio is appropriately loud for classroom while Touchpanel slider is at 50% **Note: Analog laptop audio connector will sound slightly quieter than HDMI
38 | While test audio clip plays back, press Touchpanel Mute button (near Room Audio slider): Verify no Laptop Audio goes to Program Audio speakers (front of room speakers) Verify no Laptop Audio goes to VC Codec [confirm via Bridge or Movi call] Verify no Laptop Audio goes to Echo appliance [confirm via Echo appliance monitor] Verify that Gooseneck/Revolab mic audio is still sent to room speakers Verify that Gooseneck/Revolab mic audio is still sent to VC Codec [confirm via Bridge or Movi Call] Verify that Gooseneck/Revolab mic audio is still sent to Echo appliance [confirm via Echo appliance monitor] Press Touchpanel Mute button again to return audio to fully working state
39 | Disconnect Laptop VGA/3.5mm and plug in HDMI now via Cable Cubby Should autoselect HDMI input
40 | Verify Laptop video shows on projection using HDMI input
41 | Verify Laptop audio comes through room speakers and is acceptable level w/o adjusting the Touchpanel volume slider
42 | Using a laptop, open Internet Explorer and go to https://RoomView.fau.edu . Find the e-Control tab within RoomView for this room
43 | Using the room's e-Control panel, press the Doc Cam tab Verify that room Touchpanel switches to Doc Cam tab at same time
44 | Verify Doc Cam shows on projection (Native PC Signal, Not from CODEC) and Sympodium panel Verify by disconnecting VC call [Bridge or Movi] - should see no interruption to signal on projectors and to Echo appliance After verification, reconnect VC call
45 | Verify that Doc Cam video is sent to Echo appliance [confirm via Echo appliance monitor]
46 | Verify that Doc Cam video is sent to VC Codec [confirm via Bridge or Movi Call]
47 | Verify that rear flat panel shows Confidence Monitor from Crestron CaptureHD (Laptop video w/ Instructor Camera video PIP)
48 | Verify Doc Cam controls on Touchpanel work: Zoom In / Zoom Out
49 | Press Touchpanel Blank Projection button Verify projectors are blanked Verify Sympodium panel still shows content Verify room audio is not muted Verify that no content video is sent to Echo appliance [confirm via Echo appliance monitor] Verify that no content video is sent to CODEC [confirm via Bridge or Movi Call] Verify camera video DOES get sent to Echo appliance [confirm via Echo appliance monitor] Verify camera video DOES get sent to CODEC [confirm via Bridge or Movi Call] Press Blank Projection again to return to normal projection state
50 | Press Power Off/Home, press Shutdown to turn off room equipment
51 | Verify 'please wait' screen on Touchpanel stays on long enough for projector to completely turn off
52 | Verify Touchpanel audio slider was reset to 50% after shutdown
53 | (Next steps test the expected rack power cycle behavior) Turn the system back on in any mode
54 | Go back to rack location, press Stop on Crestron CaptureHD Recorder Have Bridge Staff verify that recorded file shows camera, content Have Bridge Staff verify that recorded file contains the content audio and mic audio from earlier in the test process
55 | Stop the Ad-Hoc recording on the Echo appliance Have Bridge Staff process the Ad-Hoc recording, then verify the audio/video quality
56 | While at rack location, turn off power to all rack equipment, then turn back on power Wait 5 minutes for all equipment to return to known state from power cycle Verify that room can be started from Touchpanel as usual while the projector is already on (Ensures a power cycle returns the control system to known system off state and that the system state is not tracked by projector status)

## TestPlan-VCOriginate
No. | Test Item | Pass / Fail / Comment
VC Originate Testing
Note: "Currently-Active Video" refers to camera view that is currently being sent to other VC sites. This can be Instructor Camera, Student Camera Left, Student Camera Right, etc.
1 | At equipment rack, press Record on CaptureHD box Begin an Ad-Hoc Echo appliance recording [Echo appliance monitor] Connect to room's VC Codec [Bridge or Movi Call]
2 | Press VC Originate button on Touchpanel Verify the Touchpanel goes into a 'please wait' screen during startup Verify the Touchpanel goes to the "Select a source" after startup process is done Verify the text "VC Originate" shows near the top of the Touchpanel Verify projectors turn/stay on Verify rear flat panel turns/stays on Verify front flat panels turn/stay on
3 | Verify that room audio level was auto-set to 50% (observe volume level on Touchpanel)
4 | Verify that Far-End audio can be heard in the room and is appropriately loud at 50% on Touchpanel slider [send audio from Bridge or Movi Call]
5 | Verify that displays match the display state layout diagram for VC Originate w/ No Content
6 | Verify that Instructor Gooseneck Mic/Revolab mic audio is sent to VC Codec [confirm via Bridge or Movi Call] Verify that Instructor Gooseneck Mic/Revolab mic audio is sent to Echo appliance [confirm via Echo appliance monitor]
7 | Verify that Instructor Camera video is sent to Echo appliance [confirm via Echo appliance monitor]
8 | For each student mic in room: Activate student mic Verify student mic audio is sent to VC Codec [Bridge or Movi Call] Verify student mic audio is sent to Echo appliance [Echo appliance monitor] Verify that transition from Instructor Camera to Student Camera was smooth - less than 1 second of black interval during switch time Verify that Student Camera video is sent to VC Codec [Bridge or Movi Call] Verify that the student mic audio is audible in the other side of the room audience area (other zone) Deactivate student mic, go to next mic and repeat through all student mics in room
9 | Press PC tab on Touchpanel Verify Touchpanel shows the following text within the PC tab: "Please logon to the built-in PC using your FAU Net ID and Password"
10 | Verify that displays match the display state layout diagram for VC Originate w/ Content
11 | Verify PC shows on projection (Native PC Signal, Not from Codec) and Sympodium panel Verify by disconnecting VC call [Bridge or Movi] - should see no interruption to signal on projectors and to Echo appliance After verification, reconnect VC call
12 | On the PC, play back audio clip at http://tiny.cc/audiotest while the Windows mixer is set at 50% on the PC Verify audio is appropriately loud for classroom while Touchpanel slider is at 50%
13 | Verify that PC video is sent to Echo appliance [confirm via Echo appliance monitor] Verify that PC audio is sent to Echo appliance [confirm via Echo appliance monitor]
14 | Verify that PC video is sent to VC Codec [confirm via Bridge or Movi Call] Verify that PC audio is sent to VC Codec [confirm via Bridge or Movi Call]
15 | Verify that Currently-Active Camera video is sent to VC Codec [confirm via Bridge or Movi Call]
16 | With test audio still playing back, press Touchpanel Mute button (near Room Audio slider): Verify no PC Audio goes to Program Audio speakers (front of room speakers) Verify no PC Audio goes to VC Codec [confirm via Bridge or Movi call] Verify no PC Audio goes to Echo appliance [confirm via Echo appliance monitor] Verify that Gooseneck/Revolab mic audio is still sent to room speakers Verify that Gooseneck/Revolab mic audio is still sent to VC Codec [confirm via Bridge or Movi Call] Verify that Gooseneck/Revolab mic audio is still sent to Echo appliance [confirm via Echo appliance monitor] Press Touchpanel Mute button again to return audio to fully working state
17 | At Touchpanel, press Mute Mics button Verify projectors are blanked Verify no Gooseneck/Revolab mic audio is sent to VC Codec [confirm via Bridge or Movi Call] Verify no Gooseneck/Revolab mic audio is sent to Echo appliance [confirm via Echo appliance monitor] Verify that Touchpanel only shows a screen with "Mics are Muted - Press Screen to Continue Session"
18 | Press Mute Mics button again to disable this function Verify that Touchpanel returns to it's previous source screen Verify that projectors show content again Verify that Gooseneck/Revolab mic audio is sent to VC again [confirm via Bridge or Movi Call] Verify that Gooseneck/Revolab mic audio is sent to Echo appliance [confirm via Echo appliance monitor]
19 | Press Touchpanel Blank Projection button Verify projectors are blanked Verify Sympodium panel still shows content Verify room audio is not muted Verify that no content video is sent to Echo appliance [confirm via Echo appliance monitor] Verify that no content video is sent to CODEC [confirm via Bridge or Movi Call] Verify camera video DOES get sent to Echo appliance [confirm via Echo appliance monitor] Verify camera video DOES get sent to CODEC [confirm via Bridge or Movi Call] Press Blank Projection again to return to normal projection state
20 | Press Laptop tab on Touchpanel Verify you see the following text on the Laptop tab: "Please use one of the following resolutions with your laptop: 1024x768, 1280x720, 1280x800, 1360x768"
21 | Connect Laptop via VGA/3.5mm to system via Cable Cubby
22 | Verify on laptop that 1024x768, 1280x720, 1280x800, 1360x768 resolutions are selectable, no higher resolutions are selectable
23 | Verify that displays match the display state layout diagram for VC Originate w/ Content
24 | Verify Laptop shows on projection (Native Laptop Signal, Not from CODEC) and Sympodium panel Verify by disconnecting VC call [Bridge or Movi] - should see no interruption to signal on projectors and to Echo appliance After verification, reconnect VC call
25 | On the Laptop, play back audio clip at http://tiny.cc/audiotest while the Windows mixer is set at 50% on the Laptop Verify audio is appropriately loud for classroom while Touchpanel slider is at 50%
26 | Verify that Laptop video is sent to Echo appliance [confirm via Echo appliance monitor] Verify that Laptop audio is sent to Echo appliance [confirm via Echo appliance monitor]
27 | Verify that Laptop video is sent to VC Codec [confirm via Bridge or Movi Call] Verify that Laptop audio is sent to VC Codec [confirm via Bridge or Movi Call]
28 | Verify that Currently-Active Camera video is sent to VC Codec [confirm via Bridge or Movi Call]
29 | Disconnect Laptop VGA/3.5mm and plug in HDMI now via Cable Cubby Should autoselect HDMI input
30 | Verify Laptop video is shown on projection using HDMI input
31 | Verify Laptop audio comes through room speakers and is acceptable level w/o adjusting the Touchpanel volume slider
30 | Press Doc Cam tab on Touchpanel
31 | Verify Doc Cam shows on projection (Native PC Signal, Not from CODEC) and Sympodium panel Verify by disconnecting VC call [Bridge or Movi] - should see no interruption to signal on projectors and to Echo appliance After verification, reconnect VC call
32 | Verify that displays match the display state layout diagram for VC Originate w/ Content
33 | Verify that Doc Cam video is sent to Echo appliance [confirm via Echo appliance monitor]
34 | Verify that Doc Cam video is sent to VC Codec [confirm via Bridge or Movi Call]
35 | Verify Currently-Active Camera Video is sent to to VC Codec [Confirm via Bridge or Movi Call]
36 | Verify Doc Cam controls on Touchpanel work: Zoom In / Zoom Out
35 | Press Cameras Only tab on Touchpanel
36 | Verify that displays match the display state layout diagram for VC Originate w/ Content
37 | Verify only Currently-Active Camera video is sent to VC Codec, no duosource content [Confirm via Bridge or Movi Call]
38 | On the Touchpanel, test Camera Selection buttons: Press Left Student Camera Only button, verify camera view locks onto this camera Press Right Student Camera Only button, verify camera view locks onto this camera Press Instructor Camera Only button, verify camera view locks onto this camera Press Automatic Camera Mode button, verify that camera view returns to normal student mic-activates-camera behavior
39 | Go to each mic/camera zone in the room and activate 1 mic: Verify camera video for that zone is sent to VC Codec [Confirm via Bridge or Movi Call] Verify camera video for that zone is sent Front Flat Panels and Sympodium panel Verify that audio from that mic is sent to VC Codec [Confirm via Bridge or Movi Call] Deactivate mic, switch to next zone and repeat process
40 | Go back to rack location, press Stop on Crestron CaptureHD Recorder Have Bridge Staff verify that recorded file shows camera, content Have Bridge Staff verify that recorded file contains the content audio and mic audio from earlier in the test process
41 | Stop the Ad-Hoc recording on the Echo appliance Have Bridge Staff process the Ad-Hoc recording, then verify the audio/video quality

## TestPlan-VCReceive
No. | Test Item | Pass / Fail / Comment
VC Receive Testing
Note: "Currently-Active Video" refers to camera view that is currently being sent to other VC sites. This can be Instructor Camera, Student Camera Left, Student Camera Right, etc.
1 | Connect to room's VC Codec [Bridge or Movi Call]
2 | Press Power Off/Home button Press VC Receive button on Touchpanel Verify the Touchpanel goes into a 'Please Wait' screen during startup Verify the text "VC Receive" shows near the top of the Touchpanel Verify projectors turn/stay on Verify rear flat panel turns/stays on Verify front flat panels turn/stay on
3 | Verify that room audio level was auto-set to 50% (observe volume level on Touchpanel)
4 | Verify that Far-End audio can be heard in the room and is appropriately loud at 50% on Touchpanel slider [send audio from Bridge or Movi Call]
Verify following items while Far-End sends only Camera Video (Far-End sends No Content):
5 | Verify that displays match the display state layout diagram for VC Receive w/ No Content
6 | The system defaults to cycle between student cameras every 15 seconds while no student mics are activated: Verify switch occurs automatically Verify that cameras are in their default wide shot when shown
7 | Verify Currently-Active Camera (self-view) video is sent to VC Codec [Confirm via Bridge or Movi Call]
8 | Verify that Instructor Gooseneck Mic/Revolab mic audio is sent to VC Codec [confirm via Bridge or Movi Call]
9 | On the Touchpanel, test Camera Selection buttons Press Left Student Camera Only button, verify camera view locks onto this camera (wait at least 20 secs) Press Right Student Camera Only button, verify camera view locks onto this camera (wait at least 20 secs) Press Instructor Camera Only button, verify camera view locks onto this camera (wait at least 20 secs) Press Automatic Camera Mode button, verify that camera view returns to alternating camera view every 15 seconds
10 | Go to each mic/camera zone in the room and activate 1 mic: Verify camera video for that zone is sent to VC Codec [Confirm via Bridge or Movi Call] Verify camera video for that zone is sent Front Flat Panels and Sympodium panel Verify that audio from that mic is sent to VC Codec [Confirm via Bridge or Movi Call] Deactivate mic, switch to next zone and repeat process
Verify following items while Far-End sends Content:
11 | Verify that displays match the display state layout diagram for VC Receive w/ No Content
12 | The system defaults to cycle between student cameras every 15 seconds while no student mics are activated: Verify switch occurs automatically [Confirm via Bridge or Movi Client] Verify that cameras are in their default wide shot when shown [Confirm via Bridge or Movi Client]
13 | On the Touchpanel, test Camera Selection buttons [Confirm via Bridge or Movi Client] Press Left Student Camera Only button, verify camera view locks onto this camera (wait at least 20 secs) Press Right Student Camera Only button, verify camera view locks onto this camera (wait at least 20 secs) Press Instructor Camera Only button, verify camera view locks onto this camera (wait at least 20 secs) Press Automatic Camera Mode button, verify that camera view returns to alternating camera view every 15 seconds
14 | Go to each mic/camera zone in the room and activate 1 mic: Verify camera video for that zone is sent to VC Codec [Confirm via Bridge or Movi Call] Verify that audio from that mic is sent to VC Codec [Confirm via Bridge or Movi Call] Deactivate mic, switch to next zone and repeat process
15 | Verify that there is no Mute button on Touchpanel (should not have this capability in VC Receive mode)
16 | Verify that there is no Mute Mics button on Touchpanel (should not have this capability in VC Receive mode)
17 | Verify that there is no Blank Projection button on Touchpanel (should not have this capability in VC Receive mode)
18 | Verify there are no other tabs on the Touchpanel (Also no Advanced tab), other than VC Receive
Done with Testing in VC Receive Mode