**FAU End of Year Classroom Installation Schedule**

* Boca CM128- Install flat panel in rear of room, connected to conf monitor output on the Crestron CaptureHD
  + Morning time as Celvin is available (up until 9:30am each day)
* Boca CM130-  update room touchpanel and control program behavior to current requirements & test plan set
  + Complete work on Friday 11/16 (Room is reserved from 11AM through end of day)
* Boca NU202- Install seamless camera switcher, update room touchpanel and control program behavior to current requirements & test plan set
  + Work on Friday 11/30 (Room is reserved, all day)
  + Note that room is in use on Saturday 12/1 – confirmed with Nursing
* Boca CM125- Install seamless camera switcher, update room touchpanel and control program behavior to current requirements & test plan set
  + Work on Saturday 12/1 (Room is reserved, all day)
* Davie LA139- Full install of VC/Echo classroom to current specs
  + Room is available:
    - Saturday 11/17 - Monday 11/19
    - Wednesday 11/21 until 7pm
    - Thursday 11/22 – Monday 11/26
    - Wednesday 11/28 until 7pm
    - Friday 11/30 – Monday 12/3
    - Wednesday 12/5 until 7pm
    - Thursday 12/6 through end of year
  + Room unavailable b/c of final exams:
    - 11/29 8:00am – 10:15am
    - 11/29 10:30am – 1:00pm
    - 11/29 4:00pm – 6:30pm
    - 12/4 8:00am – 10:15am (this class session may not happen)
    - 12/5 7:00pm - 9:30pm
* Jupiter AD206- Full install of VC/Echo classroom to current specs
  + Available for work every Friday - Monday
  + Could not move any other weekday classes (Tue, Wed, Thursday)
* Boca EE106-  Update content source infrastructure to 8G, install seamless camera switcher, change mic mode to push-on/push-off, student mic speech reinforcement, update room touchpanel and control program behavior to current requirements & test plan set
  + FAU to find existing 2-channel 70V amp for ceiling speakers or 2 single channel 70v amps
  + 12/6 – 12/10 for AVI work, already reserved in room through end of year
* Boca SU117- Replace projector, equipment in Spectrum furniture
  + 12/10 – 12/12 for AVI work
* Boca FL424/427- Update to current presentation classroom spec, with Echo recording capability
  + Reserved from 12/6 through end of year
  + FAU staff to remove all equipment from furniture on 12/6
    - Keep in room: computer, rack mount power strips, speakers on front wall, 1 projector mount
    - 12/13 – 12/17 for AVI work
* Boca BU207- Update to current presentation classroom spec
  + 12/18 – 12/19 for AVI work
* Boca BU208, BU307, BU308, BU409, BU410 (FAU Boca AV Support Installations - Update room to current presentation classroom spec)
  + Replace screens as rooms are available
  + Install projector once screen in place
  + Cable pulls from instructor station to speakers, projector area as rooms are available
  + Control system configuration/program/roomview setup as time allows
  + Build racks before delivering furniture to rooms
* Boca FL411, FL432 (FAU Boca AV Support Installations - Update room to current presentation classroom spec)
  + Do after classes are out, since using existing furniture in rooms
* Jupiter SR269, SR270, SR283, SR290
  + Update to current presentation classroom spec
  + All rooms completed first week of January (need to reserve this time)
* Davie ES263- Update to current presentation classroom spec
  + Work during first week of January before classes if time allows, otherwise complete as room schedule allows early spring term
* Boca BS401B- Need quote for Bill Mclean